BRANDIX ACTION PLAN - YEAR 1

Implementation Period: April 2025 - March 2026

Document Version: 1.0 | Planning Period: April 1, 2025 - March 31, 2026
Aligned with: Brandix Strategic Plan 2025-2030
Prepared by: Brandix Operations & Implementation Team

EXECUTIVE SUMMARY

Year 1 Action Plan operationalizes Brandix Strategic Plan 2025-2030, establishing foundation for five-year transformation. Phase 1 focuses on baseline establishment, infrastructure development, and early-win achievements across all strategic pillars.

Priorities: Baseline metrics establishment, renewable energy Phase 1 (15 MW), digital transformation pilots (50% integration), foundational ESG improvements (50% sustainable materials, 92% waste recycling), organizational capacity building.

Budget: $28.5M (18% of revenue) - Environmental 42%, Digital/Innovation 28%, People 16%, Operations 11%, Governance 3%

PILLAR 1: ENVIRONMENTAL LEADERSHIP

ACTION ENV-001: Renewable Energy Expansion Phase 1

ALIGNMENT: HIGH - Direct support for "100% renewable electricity by 2030"

Objective: Install 15 MW solar capacity at 3 facilities, increase renewable mix from 50% to 55%.

Timeline:

- Q1: Engineering assessments at Seeduwa, Vishaka, Ekala; procurement, EPC contracts, grid approvals, rooftop reinforcement.

- Q2: Install 5 MW at Seeduwa, electrical upgrades, monitoring systems, maintenance training.

- Q3: Complete Vishaka and Ekala installations (5 MW each), grid synchronization, commissioning, optimization.

- Q4: Achieve 55% renewable target, post-installation audits, prepare Phase 2 plan, calculate 8,500 tCO2e reductions.

Budget: $11.5M | KPIs: 15 MW installed, 55% renewable energy, 8,500 tCO2e avoided, <5% downtime

ACTION ENV-002: Sustainable Water Management Initiative

ALIGNMENT: HIGH - Supports "50% sustainable water mix by 2030"

Objective: Expand rainwater harvesting to 5 facilities, upgrade wastewater treatment, achieve 32% sustainable water mix (from 29%).

Timeline:

- Q1: Feasibility studies for 5 facilities (Mihila, Koggala, Seeduwa, Badalgama, Pannala), design 5,000 m³/month capacity.

- Q2: Install 25 rainwater tanks (200 m³ each), civil works, integrate with distribution networks. Q3: Commission during monsoon, optimize storage, upgrade STPs at 2 facilities.

- Q4: Achieve 32% target, water balance audits, establish groundwater elimination baseline.

Budget: $3M | KPIs: 5,000 m³/month capacity, 32% sustainable water, 95% treatment efficiency

ACTION ENV-003: Sustainable Materials Sourcing Acceleration

ALIGNMENT: HIGH - Supports "75% sustainable materials by 2030"

Objective: Increase sustainable materials from 45.4% to 50% (organic cotton, recycled polyester, innovative fibers).

Timeline:

- Q1: Establish supplier scorecard (15 criteria), qualify 20 suppliers, negotiate 6,000 tons capacity.

- Q2: Procure organic cotton (1,500 tons), recycled polyester (800 tons), innovative materials (200 tons), conduct audits.

- Q3: Scale to 3,000 tons cumulative, blockchain traceability pilot (10% volume), train designers.

- Q4: Achieve 50% target (6,000 tons), publish supplier report, integrate Material Sustainability Index.

Budget: $1.5M | KPIs: 50% sustainable materials, 20 certified suppliers, 100% traceability

ACTION ENV-004: Waste Minimization & Circular Economy Pilot

ALIGNMENT: HIGH - Supports "95%+ recycling, zero landfills"

Objective: Increase recycling from 90% to 92%, achieve zero landfill, launch circular product pilots.

Timeline:

- Q1: Install waste segregation systems (15 facilities), color-coded bins, train 500 employees.

- Q2: Establish recycling partnerships, launch "Zero Waste Champion" program (50 employees), implement tracking software.

- Q3: Design fabric upcycling pilot (5 product lines), achieve 92% recycling.

- Q4: Maintain zero landfill, partner with 2 customers on take-back programs, document $0.3M savings.

Budget: $0.8M | KPIs: 92% recycling, 0% landfill, 5 upcycled products, $0.3M savings

PILLAR 2: INNOVATION & DIGITAL TRANSFORMATION

ACTION INNOV-001: Industry 4.0 Manufacturing Pilot

ALIGNMENT: HIGH - Supports "80% digital integration by 2029"

Objective: Deploy IoT sensors and AI systems across 8 production lines, achieve 50% digital integration.

Timeline:

- Q1: Select 3 pilot lines at Seeduwa, install 150 IoT sensors (temperature, vibration, productivity), deploy 10 edge computing devices.

- Q2: Develop central dashboard, train 30 operators, implement predictive maintenance algorithms.

- Q3: Deploy AI quality control with computer vision (95% accuracy target), expand to 5 more lines (250 sensors).

- Q4: Achieve 50% integration (8 of 16 lines), measure 5% efficiency and 10% downtime reduction, prepare deployment roadmap.

Budget: $3.5M | KPIs: 50% digital integration, 400 sensors, 5% efficiency gain, 95% defect detection

ACTION INNOV-002: Virtual Sampling & Digital Design Initiative

ALIGNMENT: HIGH - Supports "90% virtual sampling by 2028"

Objective: Implement 3D design software, increase virtual sampling from 20% to 40%.

Timeline:

- Q1: Procure 50 CLO3D/Browzwear licenses, set up digital studio, train 25 designers (40-hour program).

- Q2: Build digital fabric library (500 materials), create 20 virtual styles, conduct pilots with 3 brands.

- Q3: Scale to 100 styles (30% of designs), integrate with Gerber systems, reduce physical samples 20%, train 15 more designers.

- Q4: Achieve 40% virtual adoption (200 styles), measure $0.5M savings, 15% faster time-to-market, expand library to 1,000 materials.

Budget: $1.2M | KPIs: 40% virtual sampling, 200 styles, $0.5M savings, 15% faster time-to-market

ACTION INNOV-003: Innovation Center Establishment

ALIGNMENT: MODERATE - Supports "Innovation Center by 2026, 100+ innovations" but infrastructure focus

Objective: Establish innovation lab facility, launch initial R&D projects for sustainable materials.

Timeline:

- Q1: Secure 2,000 sq ft facility at Colombo HQ, procure lab equipment, hire 5 R&D specialists.

- Q2: Launch Brandix Innovation Center, establish partnerships with University of Moratuwa and SLIT, launch 5 research projects.

- Q3: Test 10 new sustainable materials (mycelium leather, ocean plastic fibers, agricultural waste textiles), launch employee innovation portal (200 ideas target).

- Q4: Complete 3 projects, launch 2 pilot products, file 2 patents, achieve 1.5% R&D investment, partner with 2 startups.

Budget: $2.5M | KPIs: Lab operational, 5 innovations, 1.5% R&D investment, 200 employee ideas

ACTION INNOV-004: ERP System Upgrade

ALIGNMENT: WEAK - IT infrastructure not in strategic objectives

Objective: Migrate legacy ERP to cloud-based InforM3 for operational efficiency and data integration.

Timeline:

- Q1: Conduct requirements analysis (Finance, HR, Procurement, Inventory), evaluate vendors, select InforM3, engage implementation partner.

- Q2: Data cleansing and migration planning, configure Finance/Accounting modules, train 50 power users, parallel testing.

- Q3: Go-live Phase 1 (Finance/Accounting), monitor performance, address integration issues, post-implementation review.

- Q4: Migrate HR and Procurement (Phase 2), achieve 80% user adoption, decommission legacy systems, document 15% faster closing, plan Phase 3.

Budget: $2M | KPIs: Phase 1 go-live, 80% adoption, 15% faster closing, zero critical incidents

PILLAR 3: PEOPLE EXCELLENCE & SOCIAL IMPACT

ACTION PEOPLE-001: Mental Health & Wellbeing Strategy

ALIGNMENT: HIGH - Supports "Mental Health Strategy (100% coverage)"

Objective: Implement comprehensive mental health program providing 100% employee access to counseling, awareness, wellness resources.

Timeline:

- Q1: Conduct needs assessment (5,000 employees), hire 3 mental health counselors, establish wellness centers at 3 facilities, launch 24/7 EAP hotline.

- Q2: Train 50 Mental Health First Aiders (40-hour certification), conduct awareness sessions (2,000 employees), offer 500 counseling sessions, launch stress management workshops.

- Q3: Expand training to 3,000 additional employees, introduce mindfulness programs, conduct Mental Health Week campaigns, monitor EAP utilization (8% target).

- Q4: Complete coverage for all 10,000 employees, achieve 100% access, conduct impact evaluation (78% wellbeing score target), publish impact report.

Budget: $1.2M | KPIs: 100% coverage, 1,500 sessions, 50 first aiders, 78% satisfaction

ACTION PEOPLE-002: Women in Leadership Development Program

ALIGNMENT: HIGH - Supports "40% women in management by 2030, IDEA Strategy"

Objective: Increase women in management from 25% to 28% through mentorship, leadership training, talent pipeline.

Timeline:

- Q1: Conduct gender diversity baseline, identify 50 high-potential women, launch mentorship (25 pairs), develop training curriculum.

- Q2: Begin 6-month leadership workshops (25 women), promote 10 women to supervisory roles, unconscious bias training (100 managers), update recruitment policies.

- Q3: Graduate first cohort (25 women), promote 8 to management (18 total YTD), launch second cohort (30 women), conduct pay equity audit.

- Q4: Achieve 28% women in management, address pay gaps (<5% target), establish Women's ERG (100 members), document success stories.

Budget: $0.8M | KPIs: 28% women in management, 18 promotions, <5% pay gap, 25 mentor pairs

ACTION PEOPLE-003: Community Impact Programs Expansion

ALIGNMENT: HIGH - Supports "Impact 1 million by 2030 (PROVIDE, EDUCATE, EMPOWER)"

Objective: Reach 450,000 beneficiaries through 75 projects under PROVIDE, EDUCATE, EMPOWER pillars.

Timeline:

- Q1: Conduct needs assessments (10 locations), launch 20 PROVIDE projects (water, sanitation, infrastructure), begin 5 EDUCATE projects (schools, scholarships), establish 3 community forums.

- Q2: Expand to 40 PROVIDE projects, support 2,000 students, launch Manusath Champion volunteer program, achieve 100,000 beneficiaries.

- Q3: Scale to 60 PROVIDE projects, launch 5 EMPOWER projects (vocational training, microfinance, entrepreneurship), conduct 3 more forums (6 total), mobilize 1,000 volunteers (10% workforce).

- Q4: Achieve 75 total projects, reach 450,000 beneficiaries, support 5,000 students, complete 10,000 volunteer hours, publish impact report.

Budget: $2.5M | KPIs: 450,000 beneficiaries, 75 projects, 5,000 students, 1,000 volunteers

ACTION PEOPLE-004: Employee Skills Development Program

ALIGNMENT: MODERATE - Supports "80 hours training/employee/year" but technical focus differs from strategic plan

Objective: Provide technical upskilling for 2,000 production employees (advanced manufacturing, quality control).

Timeline:

- Q1: Conduct skills gap analysis (cutting, sewing, finishing), develop 8-course curriculum, partner with NIBM for certifications.

- Q2: Train 500 employees (sewing technology, industrial engineering, quality control), implement apprenticeships (50 junior operators), provide industry certifications.

- Q3: Scale to 1,000 employees, launch advanced manufacturing courses (lean, 5S), conduct skills assessments, track productivity improvements.

- Q4: Complete 2,000 employees, achieve 80% certification rate, measure 3% productivity improvement, plan Year 2 digital skills focus.

Budget: $0.5M | KPIs: 2,000 trained, 80% certified, 3% productivity, 50 apprentices

PILLAR 4: OPERATIONAL EXCELLENCE

ACTION OPS-001: Quality Excellence - Six Sigma Deployment

ALIGNMENT: HIGH - Supports "Zero complaints, <0.01% defect rate"

Objective: Deploy Six Sigma and AI quality control, reduce defect rate from 0.05% to 0.03%, maintain zero complaints.

Timeline:

- Q1: Train 20 Six Sigma Green Belts and 5 Black Belts (4-week program), launch 10 DMAIC projects, establish quality dashboards.

- Q2: Complete 5 Six Sigma projects, implement AI visual inspection (3 lines, computer vision), reduce defect rate to 0.04% (20% improvement), conduct customer audits (5 customers).

- Q3: Scale AI to 10 lines, complete 8 projects YTD, achieve 98% OTD, launch Quality Excellence Awards.

- Q4: Achieve 0.03% defect rate (40% reduction), maintain zero complaints, complete 10 projects, 92% customer satisfaction, document $2M savings.

Budget: $1.5M | KPIs: 0.03% defect rate, 0 complaints, 98% OTD, 10 projects, 92% satisfaction

ACTION OPS-002: Production Capacity Expansion Phase 1

ALIGNMENT: MODERATE - Supports "30% capacity expansion" but infrastructure not detailed in strategic plan

Objective: Expand capacity by 8% through equipment and lean improvements.

Timeline:

- Q1: Capacity utilization analysis, finalize expansion for Seeduwa and Koggala (5% physical), procure 50 sewing machines and 20 cutting machines.

- Q2: Begin 2,000 sq ft civil works, install 2 new lines (100 machines), hire and train 150 operators (120-hour onboarding), commission equipment.

- Q3: Ramp up production, implement lean improvements (value stream mapping, 5S, kanban), achieve 3% productivity, monitor quality/efficiency.

- Q4: Achieve 8% total expansion (5% physical + 3% productivity), 82% OEE, prepare Year 2 plan (15% cumulative target), secure customer commitments.

Budget: $4M | KPIs: 8% capacity increase, 100 machines, 150 operators, 82% OEE

ACTION OPS-003: Supply Chain Visibility Enhancement

ALIGNMENT: WEAK - Operational supply chain improvement not in strategic objectives

Objective: Implement supply chain management platform for supplier performance tracking and delivery reliability.

Timeline:

- Q1: Assess current processes and pain points, define supplier KPIs (quality, delivery, responsiveness, sustainability), select software platform, onboard 50 critical suppliers.

- Q2: Roll out supplier portal for automated PO management and real-time tracking, implement quality tracking, conduct quarterly reviews (100 suppliers).

- Q3: Expand to 200 suppliers (80% of spend), implement delivery tracking and exception alerts, conduct 30 supplier audits, measure lead time improvements.

- Q4: Achieve 90% supplier OTD (from 82%), reduce quality defects 15%, complete 250 suppliers on platform, measure 10% faster procurement cycle.

Budget: $0.4M | KPIs: 250 suppliers, 90% OTD, 15% defect reduction, 10% faster cycle

PILLAR 5: GOVERNANCE & RISK MANAGEMENT

ACTION GOV-001: ESG Governance & Reporting Framework

ALIGNMENT: HIGH - Supports "A-level ESG rating by 2028, SLFRS S1/S2 adoption by 2026"

Objective: Implement ESG data management system, publish integrated sustainability report aligned with GRI, SASB, IFRS.

Timeline:

Q1: Implement ESG platform (Workiva or Enablon), establish monthly data collection (100+ KPIs), train 30 data champions, conduct baseline assessment (B+ rating). Q2: Conduct ESG Steering Committee meeting, initiate SLFRS S1/S2 gap analysis, engage third-party assurance provider (Deloitte or PwC). Q3: Complete mid-year ESG review, submit CDP Climate Change and Water questionnaires, conduct Board ESG training (8 directors), prepare for rating assessment (A- target). Q4: Publish Year 1 Sustainability Report (GRI, SASB, IFRS aligned), complete third-party limited assurance, achieve A- ESG rating (upgrade from B+), >95% data accuracy.

Budget: $0.8M | KPIs: A- ESG rating, report published, >95% accuracy, 100% Board trained

ACTION GOV-002: Climate Risk Assessment & Adaptation

ALIGNMENT: HIGH - Supports "Climate risk assessments (TCFD-aligned)"

Objective: Conduct comprehensive TCFD-aligned climate risk assessment, begin adaptation measures.

Timeline:

- Q1: Conduct climate risk assessment (15 facilities) identifying physical risks (flooding, water scarcity, heat) and transition risks (carbon pricing, mandates, customer requirements), establish climate risk register.

- Q2: Develop adaptation plans for 3 high-risk facilities (Mihila, Badalgama, Koggala), implement flood protection at 2 facilities, conduct scenario analysis (1.5°C, 2°C, 3°C).

- Q3: Begin physical adaptation (flood barriers, drainage, climate-resilient cooling), assess top 50 suppliers, update business continuity plans.

- Q4: Complete 50% of Year 1 adaptation investments, publish inaugural TCFD disclosure in sustainability report, conduct Board climate review, 100% facilities assessed.

Budget: $0.7M | KPIs: 100% facilities assessed, 3 adaptation plans, TCFD published, 50 suppliers assessed

ACTION GOV-003: Information Security Management System

ALIGNMENT: WEAK - IT security not in strategic plan objectives

Objective: Achieve ISO 27001 certification for IT systems protecting customer data and IP.

Timeline:

- Q1: Conduct security gap assessment against ISO 27001, identify critical assets/vulnerabilities/risks, develop ISMS documentation (policies, procedures, controls).

- Q2: Implement technical controls (firewalls, encryption, access management, vulnerability scanning), conduct security training (500 employees), establish Security Operations Center.

- Q3: Complete internal ISMS audit, remediate gaps, conduct penetration testing and vulnerability assessments, update disaster recovery plans.

- Q4: Engage ISO 27001 certification body for Stage 1 and Stage 2 audits, address findings, achieve certification, establish quarterly security reviews, zero breaches.

Budget: $0.3M | KPIs: ISO 27001 certified, 0 breaches, 500 trained, 95% patch compliance

IMPLEMENTATION GOVERNANCE

Quarterly Milestones

- Q1 (Apr-Jun 2025) FOUNDATION: Launch 25 initiatives, establish baseline metrics, award vendor contracts, commence training. Target: 10%

- Q2 (Jul-Sep 2025) ACCELERATION: Solar installations begin (5 MW), deploy digital systems (IoT, 3D design), 5,000 in training, 100K beneficiaries. Target: 40%

- Q3 (Oct-Dec 2025) EXECUTION: Complete major infrastructure, certifications in progress (ISO 50001, ISO 45001, ISO 27001), mid-year reviews, validate customer pilots. Target: 75%

- Q4 (Jan-Mar 2026) CONSOLIDATION: Finalize all initiatives, publish sustainability report, upgrade ESG to A-, complete Year 2 planning. Target: 100%

Budget Summary

| Category | Budget | % |
| --- | --- | --- |
| Environmental Leadership | $12.0M | 42% |
| Innovation & Digital | $8.0M | 28% |
| People & Social | $4.5M | 16% |
| Operational Excellence | $3.0M | 11% |
| Governance & Risk | $1.0M | 3% |
| TOTAL | $28.5M | 100% |

Success Metrics

- Environmental: 55% renewable energy, 32% sustainable water, 50% sustainable materials, 92% waste recycling

- Innovation: 50% digital integration, 40% virtual sampling, 5 innovations launched
People: 0 fatalities, 28% women in management, 100% mental health coverage, 450,000 beneficiaries

- Operations: 0 complaints, 98% on-time delivery, 0.03% defect rate, 8% capacity expansion

- Governance: A- ESG rating, sustainability report published, 100% compliance, TCFD disclosure

Document Control: Version 1.0 | Approval: December 2024 | Owner: COO | Next Review: June 2025