BRANDIX ACTION PLAN

Year 1 Implementation (April 2025 - March 2026)

Document Version: 1.0
Planning Period: April 1, 2025 - March 31, 2026
Aligned with: Brandix Strategic Plan 2025-2030
Prepared by: Brandix Operations & Implementation Team
Last Updated: November 2024

TABLE OF CONTENTS

- Action Plan Overview

- Environmental Leadership Actions

- Innovation & Digital Transformation Actions

- People Excellence & Social Impact Actions

- Operational Excellence Actions

- Governance & Risk Management Actions

- Budget Summary

- Implementation Timeline

- Monitoring & Reporting

1. ACTION PLAN OVERVIEW

Purpose

This Action Plan details the Year 1 (2025-2026) implementation of Brandix Strategic Plan 2025-2030, providing specific, executable actions with clear responsibilities, timelines, budgets, and deliverables.

Year 1 Strategic Priorities

- Establish baseline metrics and monitoring systems

- Launch foundation infrastructure projects

- Build organizational capacity for transformation

- Achieve early wins to build momentum

Year 1 Targets

- Renewable Energy: Increase from 50% to 55%

- Sustainable Water Mix: Increase from 29% to 32%

- Sustainable Materials: Increase from 45.4% to 50%

- Waste Recycling: Maintain 90%+, target 92%

- Digital Integration: Increase from 40% to 50%

- Women in Management: Increase from 25% to 28%

- Community Beneficiaries: 450,000 direct beneficiaries

Budget Allocation Year 1

Total Budget: $28.5 million (18% of projected revenue)

- Environmental: $12M (42%)

- Innovation & Digital: $8M (28%)

- People & Social: $4.5M (16%)

- Operations: $3M (11%)

- Governance: $1M (3%)

2. ENVIRONMENTAL LEADERSHIP ACTIONS

PILLAR 1: AIR - CLIMATE ACTION

ACTION ENV-AIR-001: Solar PV Installation Phase 1

Strategic Objective: Achieve 100% renewable energy by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Week 1-2: Finalize engineering designs for rooftop solar installations

- Week 3-4: Complete procurement process for 15 MW solar panels and inverters

- Week 5-8: Award contracts to installation vendors

- Week 9-12: Conduct site preparation at Seeduwa, Vishaka, and Ekala facilities

- Deliverable: Signed contracts and site-ready facilities

Q2 (July-September 2025):

- Week 1-4: Begin solar panel installation at Seeduwa facility (5 MW)

- Week 5-8: Grid connection applications submitted for all 3 facilities

- Week 9-12: Complete structural mounting and electrical work at Seeduwa

- Deliverable: Seeduwa installation 80% complete

Q3 (October-December 2025):

- Week 1-4: Commission and test Seeduwa solar installation (5 MW)

- Week 5-8: Complete installations at Vishaka (5 MW) and Ekala (5 MW)

- Week 9-12: Grid synchronization and performance testing

- Deliverable: 15 MW solar capacity operational

Q4 (January-March 2026):

- Week 1-4: Monitor performance and optimize operations

- Week 5-8: Conduct post-installation energy audits

- Week 9-12: Prepare Phase 2 expansion plan and procurement

- Deliverable: Phase 1 performance report, Phase 2 plan ready

Responsible Party:

- Project Lead: Head of Sustainability & Energy

- Project Manager: Renewable Energy Manager

- Support: Engineering (5 staff), Procurement (2 staff), Finance (1 staff)

- External: Solar EPC contractor (20 technicians)

Budget: $11.5 million

- Solar panels: $6M

- Inverters & electrical: $2.5M

- Installation labor: $1.5M

- Grid connection: $0.8M

- Project management: $0.5M

- Contingency (5%): $0.2M

KPIs & Targets:

- MW installed: 15 MW by March 2026

- Renewable energy %: Increase from 50% to 55%

- CO2 emissions avoided: 8,500 tCO2e/year

- Energy cost savings: $1.2M/year

- Installation timeline adherence: ≥95%

Dependencies:

- Government grid approvals by June 2025

- Vendor mobilization by July 2025

- No major weather disruptions during installation

- Financing disbursement on schedule

Risks & Mitigation:

- Risk: Permit delays | Mitigation: Early engagement with authorities, backup timeline

- Risk: Vendor delays | Mitigation: Performance bonds, alternative vendor list

- Risk: Grid connection issues | Mitigation: Pre-assessment, backup diesel phase-out

ACTION ENV-AIR-002: Energy Efficiency Program Launch

Strategic Objective: Reduce energy intensity by 30% by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Conduct comprehensive energy audits at all 15 facilities

- Deploy IoT energy monitoring sensors (500 units across facilities)

- Establish baseline energy consumption metrics per facility

- Train 50 energy champions across all locations

- Deliverable: Energy audit reports, baseline data established

Q2 (July-September 2025):

- Replace 3,000 conventional lights with LED (10 facilities)

- Install smart meters at 100 critical consumption points

- Launch energy awareness campaign for 10,000 employees

- Implement energy monitoring dashboard (Phase 1)

- Deliverable: 30% LED conversion, monitoring system live

Q3 (October-December 2025):

- Complete LED replacement (7,000 additional units, 5 facilities)

- Install Variable Frequency Drives (VFDs) on 50 high-consumption motors

- Begin ISO 50001 Energy Management System certification (3 pilot facilities)

- Conduct employee energy saving competition

- Deliverable: 100% LED conversion, ISO 50001 gap analysis complete

Q4 (January-March 2026):

- Optimize HVAC systems using IoT data insights

- Complete VFD installation on additional 30 motors

- Submit ISO 50001 certification applications for pilot facilities

- Analyze Year 1 energy savings and plan Year 2 initiatives

- Deliverable: 5% energy intensity reduction achieved, ISO 50001 roadmap

Responsible Party:

- Project Lead: Energy Management Team Leader

- Support: Facilities team (10 staff), IT (3 staff), HR for training (2 staff)

- External: Energy audit consultants, ISO 50001 certification body

Budget: $2.5 million

- Energy audits: $0.3M

- IoT sensors & smart meters: $0.8M

- LED lighting: $0.9M

- VFDs: $0.3M

- ISO 50001 certification: $0.1M

- Training & awareness: $0.1M

KPIs & Targets:

- Energy intensity reduction: 5% (Year 1 target)

- LED conversion: 100% of facilities

- IoT sensors deployed: 500 units

- Energy champions trained: 50 people

- ISO 50001 facilities: 3 in certification process

- Cost savings: $0.8M/year

Dependencies:

- Completion of energy audits by June 2025

- IoT infrastructure readiness

- Employee engagement in energy programs

PILLAR 2: WATER - STEWARDSHIP

ACTION ENV-WATER-001: Rainwater Harvesting Expansion

Strategic Objective: Achieve 50% sustainable water mix by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Conduct rainwater harvesting feasibility study (5 facilities)

- Design rainwater collection systems (capacity: 5,000 m³/month)

- Finalize vendor contracts for tank installation

- Begin civil works at Mihila and Koggala facilities

- Deliverable: Engineering designs approved, contracts signed

Q2 (July-September 2025):

- Install 10 rainwater harvesting tanks (500 m³ each) at 2 facilities

- Construct filtration and storage systems

- Connect to facility water distribution networks

- Train facility teams on operation and maintenance

- Deliverable: 2 facilities with operational RWH systems

Q3 (October-December 2025):

- Begin installations at 3 additional facilities (15 tanks)

- Monitor monsoon season water capture rates

- Integrate RWH data into water monitoring dashboard

- Optimize storage and distribution based on usage patterns

- Deliverable: 5 facilities with RWH, 2,500 m³ monthly capture

Q4 (January-March 2026):

- Complete all Year 1 installations

- Conduct performance evaluation of RWH systems

- Calculate sustainable water mix improvement

- Plan Year 2 expansion (10 more facilities)

- Deliverable: 32% sustainable water mix achieved, expansion plan ready

Responsible Party:

- Project Lead: Water Stewardship Manager

- Support: Engineering (4 staff), Facilities (6 staff), Operations

- External: Civil contractors, Tank suppliers

Budget: $1.8 million

- Rainwater tanks (25 units): $0.8M

- Filtration systems: $0.4M

- Civil works & installation: $0.4M

- Piping & distribution: $0.15M

- Monitoring systems: $0.05M

KPIs & Targets:

- Rainwater harvesting capacity: 5,000 m³/month

- Sustainable water mix: Increase from 29% to 32%

- Facilities with RWH: 5 facilities

- Water cost savings: $0.15M/year

- Groundwater dependency reduction: 3%

ACTION ENV-WATER-002: Wastewater Recycling Enhancement

Strategic Objective: Net-positive water operations by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Upgrade Sewage Treatment Plants (STPs) at 2 facilities

- Install advanced membrane filtration systems

- Conduct water quality baseline testing (comprehensive panel)

- Design recycled water distribution network

- Deliverable: STP upgrades 40% complete

Q2 (July-September 2025):

- Complete STP upgrades and commission new systems

- Begin recycled water production (target: 1,500 m³/month)

- Install water quality monitoring sensors (real-time)

- Train operators on advanced treatment processes

- Deliverable: 2 facilities producing recycled water

Q3 (October-December 2025):

- Expand recycled water use for cooling towers and landscaping

- Achieve 95% wastewater treatment efficiency

- Third-party water quality audit and certification

- Monitor environmental compliance metrics

- Deliverable: 1,500 m³/month recycled water utilized

Q4 (January-March 2026):

- Optimize treatment processes based on performance data

- Plan recycling expansion to 3 additional facilities

- Document case studies for stakeholder communication

- Submit environmental compliance reports

- Deliverable: Treatment efficiency >95%, compliance 100%

Responsible Party:

- Project Lead: Environmental Compliance Manager

- Support: Water treatment operators (8 staff), Lab technicians (3 staff)

- External: Water treatment technology vendors

Budget: $1.2 million

- STP upgrades: $0.7M

- Membrane filtration: $0.3M

- Water quality monitoring: $0.1M

- Training & certification: $0.1M

KPIs & Targets:

- Recycled water production: 1,500 m³/month

- Treatment efficiency: >95%

- Water quality compliance: 100%

- Third-party audits: 2 facilities certified

PILLAR 3: EARTH - CIRCULAR ECONOMY

ACTION ENV-EARTH-001: Sustainable Materials Sourcing Program

Strategic Objective: Source 75% sustainable materials by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Establish supplier sustainability scorecard criteria

- Conduct baseline assessment of current material sources

- Identify and qualify 15 new sustainable material suppliers

- Negotiate contracts with organic cotton suppliers (5,000 tons/year)

- Deliverable: Supplier scorecard launched, 15 suppliers qualified

Q2 (July-September 2025):

- Begin procurement of organic cotton (1,200 tons)

- Source recycled polyester (800 tons)

- Pilot Tencel and other innovative materials (200 tons)

- Update supplier database with sustainability certifications

- Deliverable: 2,200 tons sustainable materials procured

Q3 (October-December 2025):

- Expand organic cotton procurement (1,500 tons)

- Increase recycled polyester orders (1,000 tons)

- Conduct supplier sustainability audits (10 suppliers)

- Integrate sustainable materials into design process

- Deliverable: 4,700 tons total sustainable materials YTD

Q4 (January-March 2026):

- Finalize Year 1 sustainable material procurement (6,000 tons)

- Achieve 50% sustainable materials target

- Publish supplier sustainability performance report

- Plan Year 2 procurement strategy (target: 58%)

- Deliverable: 50% sustainable materials achieved

Responsible Party:

- Project Lead: Head of Procurement

- Support: Sourcing team (8 staff), Quality assurance (3 staff), Design (2 staff)

- External: Certification bodies, Supplier auditors

Budget: $1.5 million (premium over conventional materials)

- Organic cotton premium: $0.9M

- Recycled polyester premium: $0.4M

- Material testing & certification: $0.15M

- Supplier audits: $0.05M

KPIs & Targets:

- Sustainable materials %: Increase from 45.4% to 50%

- Tons sustainable materials: 6,000 tons

- Certified suppliers: 15 new suppliers

- Supplier audits completed: 10 audits

- Material quality compliance: 100%

ACTION ENV-EARTH-002: Waste Reduction and Recycling Initiative

Strategic Objective: Achieve 95%+ waste recycling by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Install waste segregation systems at all 15 facilities

- Deploy 200 color-coded waste bins

- Train 500 employees on waste segregation protocols

- Establish contracts with recycling partners (fabric, plastic, metal)

- Deliverable: Waste infrastructure in place, team trained

Q2 (July-September 2025):

- Launch "Zero Waste Champions" program (50 champions)

- Implement fabric waste upcycling pilot (3 product lines)

- Begin monthly waste audits at all facilities

- Install waste tracking software system

- Deliverable: Upcycling pilot products launched

Q3 (October-December 2025):

- Achieve 92% waste recycling rate

- Scale upcycling program (5 additional product lines)

- Partner with 2 customers on circular take-back programs

- Conduct waste reduction competition among facilities

- Deliverable: 92% recycling rate achieved

Q4 (January-March 2026):

- Maintain zero waste to landfill across all facilities

- Document waste reduction case studies

- Calculate cost savings from waste reduction

- Plan Year 2 circular economy innovations

- Deliverable: Zero landfill waste maintained, 92% recycling

Responsible Party:

- Project Lead: Waste Management Coordinator

- Support: Facilities team (12 staff), Operations supervisors (15 staff)

- External: Recycling partners, Upcycling designers

Budget: $0.8 million

- Waste segregation infrastructure: $0.3M

- Upcycling program setup: $0.2M

- Waste tracking system: $0.15M

- Training & awareness: $0.1M

- Recycling partnerships: $0.05M

KPIs & Targets:

- Waste recycling rate: 92% (from 90%)

- Waste to landfill: 0%

- Waste champions trained: 50 people

- Upcycled product lines: 8 products

- Cost savings from waste reduction: $0.3M/year

3. INNOVATION & DIGITAL TRANSFORMATION ACTIONS

PILLAR 4: DIGITAL MANUFACTURING

ACTION INNOV-DIGITAL-001: IoT and Industry 4.0 Pilot

Strategic Objective: Achieve 80% digital integration by 2029

Quarterly Activities:

Q1 (April-June 2025):

- Select 3 pilot production lines for IoT deployment

- Procure and install 150 IoT sensors (machine monitoring)

- Deploy edge computing devices (10 units)

- Establish data collection and analytics infrastructure

- Deliverable: Pilot lines identified, sensors installed

Q2 (July-September 2025):

- Connect machines to central monitoring dashboard

- Train 30 operators and supervisors on digital systems

- Begin real-time production monitoring and data collection

- Implement predictive maintenance algorithms (pilot)

- Deliverable: Real-time monitoring operational

Q3 (October-December 2025):

- Analyze 6 months of production data

- Implement AI-powered quality control on 1 pilot line

- Deploy automated defect detection (computer vision)

- Optimize production parameters using data insights

- Deliverable: AI quality control live, 5% efficiency gain

Q4 (January-March 2026):

- Scale IoT to 5 additional production lines (250 more sensors)

- Achieve 50% digital integration target

- Document ROI and prepare full-scale deployment plan

- Plan Year 2 expansion (15 more lines)

- Deliverable: 50% digital integration achieved

Responsible Party:

- Project Lead: Director of Digital Transformation

- Support: IT team (6 staff), Production (10 staff), Data analytics (3 staff)

- External: IoT platform vendor, AI consultants

Budget: $3.5 million

- IoT sensors & hardware: $1.2M

- Edge computing devices: $0.5M

- Software platforms & licenses: $0.8M

- AI/ML development: $0.6M

- Training: $0.3M

- Consulting: $0.1M

KPIs & Targets:

- Digital integration: Increase from 40% to 50%

- IoT sensors deployed: 400 sensors

- Production lines monitored: 8 lines

- Production efficiency gain: 5%

- Defect detection accuracy: 95%

- Downtime reduction: 10%

ACTION INNOV-DIGITAL-002: 3D Design and Virtual Sampling

Strategic Objective: 90% virtual sampling adoption by 2028

Quarterly Activities:

Q1 (April-June 2025):

- Procure 3D design software licenses (50 seats)

- Set up digital design studio with workstations

- Train 25 designers on 3D modeling tools

- Establish digital fabric library (500 materials)

- Deliverable: Design studio operational, team trained

Q2 (July-September 2025):

- Begin 3D design for new product lines (20 styles)

- Create virtual samples for customer presentations

- Integrate 3D designs with pattern-making systems

- Conduct customer pilots with 3 major brands

- Deliverable: 20 virtual samples created, customer feedback

Q3 (October-December 2025):

- Scale virtual sampling to 100 styles (30% of new designs)

- Reduce physical sample production by 20%

- Expand digital fabric library to 1,000 materials

- Train additional 15 designers (total 40)

- Deliverable: 30% virtual sampling rate achieved

Q4 (January-March 2026):

- Achieve 40% virtual sampling rate (200 styles)

- Measure time and cost savings from reduced physical sampling

- Establish customer virtual approval processes

- Plan Year 2 expansion (target: 60% virtual sampling)

- Deliverable: 40% virtual sampling, $0.5M cost savings

Responsible Party:

- Project Lead: Head of Design & Product Development

- Support: Design team (40 staff), IT (2 staff), Customer service (3 staff)

- External: 3D software vendor, Training consultants

Budget: $1.2 million

- Software licenses: $0.5M

- Hardware (workstations): $0.3M

- Digital fabric library: $0.2M

- Training: $0.15M

- Customer pilot programs: $0.05M

KPIs & Targets:

- Virtual sampling adoption: 40% (from 20%)

- Virtual samples created: 200 styles

- Physical samples reduced: 20%

- Time-to-market reduction: 15%

- Sample cost savings: $0.5M/year

- Designers trained: 40 people

ACTION INNOV-DIGITAL-003: Innovation Lab Establishment

Strategic Objective: Launch 100+ innovations annually

Quarterly Activities:

Q1 (April-June 2025):

- Secure innovation lab facility (2,000 sq ft)

- Procure equipment (testing machines, prototyping tools)

- Hire 5 R&D specialists (materials, technology, sustainability)

- Establish partnerships with 2 universities

- Deliverable: Lab facility ready, team hired

Q2 (July-September 2025):

- Launch innovation lab officially

- Begin 5 research projects (sustainable materials focus)

- Establish employee innovation submission portal

- Conduct first innovation challenge (company-wide)

- Deliverable: Lab operational, 5 projects in progress

Q3 (October-December 2025):

- Complete 3 innovation projects, launch 2 pilot products

- Test 10 new sustainable material samples

- Receive 200 employee innovation ideas

- Partner with 2 material science startups

- Deliverable: 2 innovations launched, 10 materials tested

Q4 (January-March 2026):

- Launch 5 total innovations in Year 1

- File 2 patent applications

- Invest 1.5% of revenue in R&D (target: 3% by 2030)

- Plan Year 2 innovation portfolio (15 innovations target)

- Deliverable: 5 innovations launched, innovation pipeline established

Responsible Party:

- Project Lead: Head of Innovation & R&D

- R&D Team: 5 specialists, 2 lab technicians

- Support: Design (3 staff), Marketing (2 staff)

- External: University partners, Startup collaborators

Budget: $2.5 million

- Lab facility setup: $0.8M

- Equipment & tools: $0.6M

- R&D salaries: $0.7M

- Materials & testing: $0.2M

- Partnerships & collaborations: $0.15M

- IP & patents: $0.05M

KPIs & Targets:

- Innovations launched: 5 innovations

- R&D investment: 1.5% of revenue

- Patent applications: 2 filed

- Employee ideas submitted: 200 ideas

- University partnerships: 2 active collaborations

- Startup collaborations: 2 partnerships

4. PEOPLE EXCELLENCE & SOCIAL IMPACT ACTIONS

PILLAR 5: EMPLOYEE WELLBEING

ACTION PEOPLE-WELL-001: Mental Health Strategy Implementation

Strategic Objective: 100% employee wellbeing program coverage

Quarterly Activities:

Q1 (April-June 2025):

- Conduct mental health needs assessment (5,000 employees surveyed)

- Hire 3 mental health counselors and establish wellness centers

- Develop mental health awareness training curriculum

- Launch Employee Assistance Program (EAP) with 24/7 hotline

- Deliverable: EAP launched, wellness centers established

Q2 (July-September 2025):

- Train 50 mental health first aiders across all facilities

- Conduct mental health awareness sessions (2,000 employees)

- Offer confidential counseling (target: 500 sessions)

- Launch stress management workshops (10 sessions)

- Deliverable: 2,000 employees trained, 500 counseling sessions

Q3 (October-December 2025):

- Expand awareness training (additional 3,000 employees)

- Introduce mindfulness and meditation programs

- Conduct mental health week campaigns (all facilities)

- Monitor EAP utilization and feedback

- Deliverable: 5,000 employees reached, programs running

Q4 (January-March 2026):

- Complete training for remaining 5,000 employees

- Achieve 100% employee access to mental health resources

- Conduct Year 1 program evaluation and impact study

- Plan Year 2 enhancements based on feedback

- Deliverable: 100% coverage achieved, impact report published

Responsible Party:

- Project Lead: Head of HR & Employee Wellbeing

- Support: HR team (8 staff), Counselors (3 staff), Trainers (5 staff)

- External: Mental health consultants, EAP provider

Budget: $1.2 million

- Counselor salaries: $0.4M

- EAP service provider: $0.3M

- Wellness center setup: $0.2M

- Training programs: $0.2M

- Awareness campaigns: $0.1M

KPIs & Targets:

- Employee coverage: 100% access to mental health resources

- Employees trained: 10,000 people

- Counseling sessions: 1,500 sessions/year

- Mental health first aiders: 50 trained

- Employee satisfaction (wellbeing): Increase to 78%

- EAP utilization rate: 8% of workforce

ACTION PEOPLE-WELL-002: Health & Safety Excellence Program

Strategic Objective: Zero fatalities and high-consequence injuries

Quarterly Activities:

Q1 (April-June 2025):

- Conduct comprehensive safety audits (all 15 facilities)

- Upgrade safety equipment and PPE (10,000 employees)

- Launch "Safety First" awareness campaign

- Train 100 safety officers and committee members

- Deliverable: Safety audits complete, equipment upgraded

Q2 (July-September 2025):

- Implement behavior-based safety observation program

- Install 200 safety monitoring cameras at high-risk areas

- Conduct emergency evacuation drills (all facilities)

- Launch near-miss reporting mobile app

- Deliverable: Monitoring systems installed, drills completed

Q3 (October-December 2025):

- Achieve 50% increase in proactive hazard reporting

- Conduct advanced safety training for machine operators (500 people)

- Implement ergonomic improvements (50 workstations)

- Perform third-party safety certification audits

- Deliverable: Hazard reporting +50%, certifications in progress

Q4 (January-March 2026):

- Maintain zero fatalities and zero high-consequence injuries

- Begin ISO 45001 certification process (3 pilot facilities)

- Conduct Year 1 safety performance review

- Plan Year 2 safety initiatives

- Deliverable: Zero harm achieved, ISO 45001 gap analysis done

Responsible Party:

- Project Lead: Head of Health, Safety & Environment (HSE)

- Support: Safety officers (25 staff), Facilities (10 staff), Training (5 staff)

- External: Safety consultants, ISO 45001 auditors

Budget: $1.8 million

- Safety equipment & PPE: $0.8M

- Monitoring systems: $0.4M

- Training programs: $0.3M

- ISO 45001 certification: $0.15M

- Ergonomic improvements: $0.15M

KPIs & Targets:

- Fatalities: 0

- High-consequence injuries: 0

- Lost-time injury frequency rate: <0.5

- Hazard reports: +50% increase

- Safety training hours: 40,000 hours

- ISO 45001 facilities: 3 in certification process

- Safety audit score: >90%

PILLAR 6: DIVERSITY & INCLUSION

ACTION PEOPLE-DEI-001: Women in Management Development Program

Strategic Objective: Achieve 40% women in management by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Conduct gender diversity baseline assessment

- Identify 50 high-potential women for leadership pipeline

- Launch women's mentorship program (25 mentor-mentee pairs)

- Develop leadership training curriculum (gender-inclusive)

- Deliverable: Pipeline identified, mentorship program launched

Q2 (July-September 2025):

- Begin leadership development workshops (25 women, 6-month program)

- Promote 10 women to supervisory roles

- Conduct unconscious bias training for 100 managers

- Review and update recruitment policies for gender equity

- Deliverable: 10 promotions, training programs running

Q3 (October-December 2025):

- Graduate first cohort of leadership program (25 women)

- Promote 8 women to management positions

- Launch second cohort of leadership program (30 women)

- Conduct gender pay equity audit across all levels

- Deliverable: 18 total promotions YTD, pay equity audit complete

Q4 (January-March 2026):

- Achieve 28% women in management (from 25%)

- Address identified pay equity gaps (target: <5% gap)

- Establish women's employee resource group (ERG)

- Plan Year 2 targets (32% women in management)

- Deliverable: 28% women in management achieved

Responsible Party:

- Project Lead: Head of Diversity, Equity & Inclusion

- Support: HR (6 staff), Learning & Development (3 staff), Senior leaders as mentors (25)

- External: Leadership development consultants

Budget: $0.8 million

- Leadership training programs: $0.4M

- Mentorship program: $0.1M

- Unconscious bias training: $0.15M

- Pay equity adjustments: $0.1M

- ERG support: $0.05M

KPIs & Targets:

- Women in management: Increase from 25% to 28%

- Women in leadership pipeline: 50 identified

- Women promoted: 18 promotions

- Managers trained (unconscious bias): 100 managers

- Gender pay gap: Reduce to <5%

- Mentorship pairs: 25 active pairs

PILLAR 7: COMMUNITY IMPACT

ACTION PEOPLE-COMMUNITY-001: Community Development Programs

Strategic Objective: Impact 1 million community members by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Conduct community needs assessments (10 locations)

- Launch 20 PROVIDE projects (water, sanitation, infrastructure)

- Begin 5 EDUCATE projects (school infrastructure, scholarships)

- Establish community forums (3 locations, 100 participants)

- Deliverable: 25 projects launched, forums established

Q2 (July-September 2025):

- Expand PROVIDE projects to 40 total projects

- Support 2,000 students with educational assistance

- Launch Brandix Manusath Champion volunteer program

- Complete 100,000 direct beneficiaries milestone

- Deliverable: 40 projects running, 100K beneficiaries

Q3 (October-December 2025):

- Scale to 60 total PROVIDE projects

- Launch 5 EMPOWER projects (vocational training, microfinance)

- Conduct additional 3 community forums (total 6)

- Mobilize 1,000 employee volunteers (10% of workforce)

- Deliverable: 60 projects, 6 forums, volunteer program active

Q4 (January-March 2026):

- Achieve 75 total community projects for Year 1

- Reach 450,000 direct beneficiaries (from 400,000)

- Support 5,000 students through education initiatives

- Conduct impact evaluation study

- Deliverable: 450K beneficiaries, impact report published

Responsible Party:

- Project Lead: Head of Corporate Social Responsibility

- Support: CSR team (8 staff), HR for volunteers (2 staff), Finance (1 staff)

- External: NGO partners, Community leaders

Budget: $2.5 million

- PROVIDE projects: $1.5M

- EDUCATE projects: $0.6M

- EMPOWER projects: $0.3M

- Community forums: $0.05M

- Volunteer program: $0.05M

KPIs & Targets:

- Total community projects: 75 projects

- Direct beneficiaries: 450,000 people

- Students supported: 5,000 students

- Community forums: 6 forums, 200+ participants

- Employee volunteers: 1,000 volunteers (10% of workforce)

- Volunteer hours: 10,000 hours

5. OPERATIONAL EXCELLENCE ACTIONS

PILLAR 8: QUALITY MANAGEMENT

ACTION OPS-QUALITY-001: Six Sigma Deployment

Strategic Objective: Achieve <0.01% quality defect rate

Quarterly Activities:

Q1 (April-June 2025):

- Train 20 Six Sigma Green Belts

- Train 5 Six Sigma Black Belts

- Launch 10 quality improvement projects across facilities

- Establish quality control dashboards (real-time monitoring)

- Deliverable: Team trained, projects initiated

Q2 (July-September 2025):

- Complete 5 Six Sigma projects (DMAIC methodology)

- Implement AI-powered quality inspection on 3 production lines

- Reduce defect rate by 20% (from 0.05% to 0.04%)

- Conduct customer quality audits (5 major customers)

- Deliverable: 5 projects completed, 20% defect reduction

Q3 (October-December 2025):

- Scale AI quality inspection to 10 production lines

- Complete 8 total Six Sigma projects YTD

- Achieve 98% on-time delivery performance

- Launch quality excellence awards program

- Deliverable: 98% OTD, AI on 10 lines

Q4 (January-March 2026):

- Complete 10 total Six Sigma projects for Year 1

- Achieve 0.03% defect rate (40% reduction)

- Maintain zero customer complaints

- Plan Year 2 quality initiatives (target: 0.02% defect rate)

- Deliverable: Zero complaints, 0.03% defect rate

Responsible Party:

- Project Lead: Head of Quality Assurance

- Support: Quality team (30 staff), Six Sigma experts (5 staff), IT (2 staff)

- External: Six Sigma trainers, AI quality inspection vendor

Budget: $1.5 million

- Six Sigma training & certification: $0.4M

- AI quality inspection systems: $0.8M

- Quality monitoring tools: $0.2M

- Awards & recognition: $0.1M

KPIs & Targets:

- Quality defect rate: Reduce from 0.05% to 0.03%

- Customer complaints: 0

- On-time delivery: 98%

- Six Sigma projects: 10 completed

- Six Sigma certified: 20 Green Belts, 5 Black Belts

- AI inspection lines: 10 lines

- Customer satisfaction: 92%

ACTION OPS-CAPACITY-001: Production Capacity Expansion

Strategic Objective: Expand capacity by 30% by 2030

Quarterly Activities:

Q1 (April-June 2025):

- Conduct capacity utilization analysis (all facilities)

- Finalize expansion plan for 2 facilities (5% capacity increase)

- Procure 50 new sewing machines and equipment

- Begin civil works for facility expansion (2,000 sq ft)

- Deliverable: Expansion plan approved, procurement initiated

Q2 (July-September 2025):

- Install new production lines (2 lines, 100 machines)

- Hire and train 150 new operators

- Commission expanded capacity (5% increase)

- Optimize production scheduling for increased output

- Deliverable: 5% capacity increase operational

Q3 (October-December 2025):

- Ramp up production to utilize new capacity

- Implement lean manufacturing improvements (reduce waste)

- Achieve 3% productivity improvement through optimization

- Monitor quality and efficiency metrics

- Deliverable: Full capacity utilization, 3% productivity gain

Q4 (January-March 2026):

- Achieve 8% total capacity expansion (5% physical + 3% productivity)

- Document learnings and ROI

- Plan Year 2 expansion (10% additional capacity target)

- Secure customer commitments for increased capacity

- Deliverable: 8% capacity increase, Year 2 plan ready

Responsible Party:

- Project Lead: Head of Operations

- Support: Production managers (10 staff), Engineering (5 staff), HR (3 staff)

- External: Equipment suppliers, Construction contractors

Budget: $4 million

- New machines & equipment: $2.5M

- Facility expansion (civil works): $1M

- Recruitment & training: $0.3M

- Lean manufacturing tools: $0.2M

KPIs & Targets:

- Capacity expansion: 8% (Year 1 target)

- New production lines: 2 lines

- New machines: 100 machines

- New employees: 150 operators

- Productivity improvement: 3%

- Overall Equipment Effectiveness (OEE): 82%

6. GOVERNANCE & RISK MANAGEMENT ACTIONS

PILLAR 9: ESG GOVERNANCE

ACTION GOV-ESG-001: ESG Monitoring and Reporting System

Strategic Objective: Achieve A-level ESG rating by 2028

Quarterly Activities:

Q1 (April-June 2025):

- Implement ESG data management platform

- Establish data collection protocols for all KPIs

- Train 30 data champions across departments

- Conduct baseline ESG assessment (current rating: B+)

- Deliverable: ESG platform operational, baseline established

Q2 (July-September 2025):

- Begin monthly ESG data collection and validation

- Conduct first ESG Steering Committee quarterly review

- Initiate SLFRS S1 and S2 gap analysis

- Engage third-party for sustainability report assurance

- Deliverable: Q1 ESG performance report, SLFRS gap analysis

Q3 (October-December 2025):

- Complete mid-year ESG performance review

- Submit CDP Climate Change and Water disclosure

- Conduct Board-level ESG training (all 8 directors)

- Prepare for external ESG rating assessment

- Deliverable: CDP submission, Board trained

Q4 (January-March 2026):

- Publish Year 1 Sustainability Report (GRI, SASB, IFRS aligned)

- Complete third-party assurance of ESG data

- Achieve improved ESG rating (target: A-)

- Plan Year 2 ESG roadmap

- Deliverable: Sustainability report published, A- rating achieved

Responsible Party:

- Project Lead: ESG Director

- Support: ESG team (6 staff), IT (2 staff), Finance (2 staff), Communications (2 staff)

- External: ESG platform vendor, Assurance provider, Rating agencies

Budget: $0.8 million

- ESG platform software: $0.3M

- Third-party assurance: $0.15M

- CDP participation: $0.05M

- Report design & publication: $0.15M

- Board training: $0.05M

- Rating agency fees: $0.1M

KPIs & Targets:

- ESG rating: Improve from B+ to A-

- Data collection accuracy: >95%

- ESG Steering Committee meetings: 4 meetings

- Board ESG training: 100% of directors

- Sustainability report: Published on time

- Third-party assurance: Obtained

- CDP score: B or higher

ACTION GOV-RISK-001: Climate Risk Assessment and Management

Strategic Objective: Full climate resilience by 2028

Quarterly Activities:

Q1 (April-June 2025):

- Conduct TCFD-aligned climate risk assessment (all facilities)

- Identify physical risks (flooding, water stress, extreme heat)

- Identify transition risks (carbon pricing, regulations)

- Establish climate risk register and scoring methodology

- Deliverable: Climate risk assessment complete

Q2 (July-September 2025):

- Develop climate adaptation plans for high-risk facilities (3 facilities)

- Implement flood protection measures (2 facilities)

- Conduct climate scenario analysis (1.5°C, 2°C, 3°C scenarios)

- Integrate climate risks into enterprise risk management

- Deliverable: Adaptation plans ready, scenario analysis done

Q3 (October-December 2025):

- Begin implementation of adaptation measures (flood barriers, cooling systems)

- Conduct supplier climate risk assessment (top 50 suppliers)

- Update business continuity plans with climate scenarios

- Train risk management team on climate risks

- Deliverable: Adaptation measures 50% complete

Q4 (January-March 2026):

- Complete Year 1 climate adaptation investments

- Publish TCFD disclosure in sustainability report

- Conduct Board-level climate risk review

- Plan Year 2 climate resilience initiatives

- Deliverable: TCFD disclosure published, Board briefed

Responsible Party:

- Project Lead: Head of Enterprise Risk Management

- Support: Risk team (4 staff), Sustainability (3 staff), Facilities (5 staff)

- External: Climate risk consultants, TCFD advisors

Budget: $0.7 million

- Climate risk assessment: $0.2M

- Adaptation measures (flood protection, cooling): $0.35M

- Scenario analysis & modeling: $0.1M

- Training & capacity building: $0.05M

KPIs & Targets:

- Climate risk assessment: 100% facilities assessed

- High-risk facilities with adaptation plans: 3 facilities

- Adaptation measures implemented: 50% complete

- TCFD disclosure: Published

- Supplier climate assessment: 50 suppliers assessed

- Business continuity plan update: 100% complete

7. BUDGET SUMMARY - YEAR 1 (2025-2026)

Total Budget: $28.5 Million

| Category | Budget ($M) | % of Total | Key Investments |
| --- | --- | --- | --- |
| Environmental Leadership | $12.0M | 42% |  |
| - Air (Renewable Energy & Efficiency) | $14.0M | 49% | Solar PV, LED, VFDs, R-22 phase-out |
| - Water (Harvesting & Recycling) | $3.0M | 11% | RWH systems, STP upgrades |
| - Earth (Materials & Waste) | $2.3M | 8% | Sustainable materials, recycling infrastructure |
| Innovation & Digital | $8.0M | 28% |  |
| - Digital Manufacturing | $3.5M | 12% | IoT, Industry 4.0, AI quality control |
| - 3D Design & Virtual Sampling | $1.2M | 4% | 3D software, digital fabric library |
| - Innovation Lab | $2.5M | 9% | Lab setup, R&D projects |
| - Automation | $0.8M | 3% | Robotics, automated systems |
| People & Social Impact | $4.5M | 16% |  |
| - Employee Wellbeing | $3.0M | 11% | Mental health, safety programs |
| - Diversity & Inclusion | $0.8M | 3% | Women in management, training |
| - Community Programs | $2.5M | 9% | PROVIDE, EDUCATE, EMPOWER projects |
| Operational Excellence | $3.0M | 11% |  |
| - Quality Management | $1.5M | 5% | Six Sigma, AI inspection |
| - Capacity Expansion | $4.0M | 14% | New equipment, facility expansion |
| Governance & Risk | $1.0M | 3% |  |
| - ESG Systems | $0.8M | 3% | ESG platform, reporting, assurance |
| - Climate Risk Management | $0.7M | 2% | Risk assessment, adaptation measures |
| TOTAL | $28.5M | 100% |  |

Funding Sources

| Source | Amount ($M) | % of Total |
| --- | --- | --- |
| Operational Cash Flow | $17.1M | 60% |
| Green Financing/Sustainability Loans | $7.1M | 25% |
| Partnerships & Grants | $2.9M | 10% |
| Asset Optimization | $1.4M | 5% |
| TOTAL | $28.5M | 100% |

8. IMPLEMENTATION TIMELINE - YEAR 1

Quarterly Milestone Summary

Q1 (April-June 2025) - FOUNDATION

- Complete all baseline assessments and audits

- Launch 25 major initiatives across all pillars

- Establish monitoring systems and dashboards

- Secure vendor contracts and partnerships

- Target Achievement: 10% of Year 1 goals

Q2 (July-September 2025) - ACCELERATION

- Scale renewable energy installations (5 MW)

- Deploy IoT systems and digital tools

- Launch employee training programs (5,000+ employees)

- Begin community projects (40 projects)

- Target Achievement: 40% of Year 1 goals

Q3 (October-December 2025) - EXECUTION

- Complete major infrastructure projects

- Achieve mid-year performance targets

- Conduct performance reviews and adjustments

- Prepare for Year-end assessments

- Target Achievement: 75% of Year 1 goals

Q4 (January-March 2026) - CONSOLIDATION

- Finalize all Year 1 initiatives

- Conduct comprehensive evaluation

- Publish sustainability report

- Plan Year 2 activities

- Target Achievement: 100% of Year 1 goals

Critical Path Activities

Must Complete by Q2 2025:

- Renewable energy vendor contracts

- ESG data platform operational

- Safety equipment upgrades

- Supplier sustainability assessments

Must Complete by Q4 2025:

- Solar PV installations (15 MW)

- Digital integration (50%)

- Sustainable materials (50%)

- Mental health program (100% coverage)

Must Complete by Q4 2026:

- All Year 1 KPI targets

- Sustainability report published

- Third-party assurance obtained

- Year 2 action plan approved

9. MONITORING & REPORTING FRAMEWORK

Performance Monitoring

Daily Monitoring:

- Production output and quality metrics

- Safety incidents and near-misses

- Energy and water consumption

- Machine performance (IoT data)

Weekly Monitoring:

- Project progress updates (all 50+ initiatives)

- Budget vs. actual spending

- KPI dashboard review

- Issue log and risk register

Monthly Monitoring:

- Department performance reviews

- Financial statements and variance analysis

- Stakeholder feedback collection

- Executive management reports

Quarterly Monitoring:

- ESG Steering Committee review

- Strategic KPI assessment

- Board reporting

- External stakeholder updates

Reporting Structure

Internal Reports:

- Weekly: Project status reports to department heads

- Monthly: Performance dashboards to executive team

- Quarterly: Comprehensive ESG report to Board

External Reports:

- Quarterly: Customer sustainability updates

- Semi-Annual: Investor and stakeholder briefings

- Annual: Sustainability report (public)

Key Performance Dashboards

Environmental Dashboard:

- Renewable energy % (target: 55%)

- Sustainable water mix % (target: 32%)

- Sustainable materials % (target: 50%)

- Waste recycling rate % (target: 92%)

- GHG emissions (tCO2e)

Innovation Dashboard:

- Digital integration % (target: 50%)

- Virtual sampling % (target: 40%)

- Innovations launched (#)

- R&D investment (% of revenue)

People Dashboard:

- Women in management % (target: 28%)

- Training hours per employee

- Safety metrics (LTIFR, incidents)

- Employee satisfaction score

- Community beneficiaries (#)

Operations Dashboard:

- Customer complaints (#, target: 0)

- On-time delivery % (target: 98%)

- Quality defect rate (target: 0.03%)

- Capacity utilization %

- Productivity improvement %

Governance Dashboard:

- ESG rating score

- Compliance violations (#, target: 0)

- Risk incidents (#)

- Audit findings (#)

Success Criteria - Year 1

Environmental: ✓ 55% renewable energy achieved ✓ 32% sustainable water mix achieved ✓ 50% sustainable materials achieved ✓ 92% waste recycling achieved ✓ Zero environmental violations

Innovation: ✓ 50% digital integration achieved ✓ 40% virtual sampling achieved ✓ 5 innovations launched ✓ Innovation lab operational

People: ✓ Zero fatalities and high-consequence injuries ✓ 28% women in management achieved ✓ 100% mental health coverage ✓ 450,000 community beneficiaries

Operations: ✓ Zero customer complaints ✓ 98% on-time delivery ✓ 0.03% defect rate ✓ 8% capacity expansion

Governance: ✓ A- ESG rating achieved ✓ Sustainability report published ✓ 100% compliance maintained ✓ Climate risk assessment complete

CONCLUSION

This Year 1 Action Plan provides a comprehensive roadmap for implementing Brandix's strategic priorities during 2025-2026. With a $28.5 million investment across 50+ initiatives, we are positioned to achieve significant progress toward our 2030 vision.

Key Success Factors:

- Strong project management and governance

- Cross-functional collaboration

- Employee engagement and capability building

- Vendor and partner performance

- Adequate funding and resource allocation

- Regular monitoring and adaptive management

Next Steps:

- Obtain Board approval for Action Plan and budget

- Communicate plan to all stakeholders

- Mobilize project teams and resources

- Launch initiatives according to quarterly schedule

- Monitor progress and report regularly

By executing this Action Plan with excellence, we will build a strong foundation for our 5-year strategic transformation journey.

Document Control:

- Version: 1.0

- Approval Date: December 2024

- Implementation Start: April 1, 2025

- Approved by: Executive Leadership Team

- Owner: Chief Operating Officer

- Distribution: All Department Heads, Project Leads

"Turning Strategy into Action - Year 1 Execution Excellence"